## Risk-Assessment.xlsx
Risk ID | Asset | Threat | Vulnerability | Risk | Likelihood | Impact | Treatment | Proposed Control
R-001 | Employee Data | Insider / Attacker | Some administrator accounts do not use MFA | Data breach or unauthorized access | High | High | Mitigate | MFA; stronger password requirements
R-002 | Employee Data | Insider / Attacker | Excessive administrator accounts / privileges | Data leakage, unauthorized modification or access | High | High | Mitigate | Least privilege; RBAC; periodic access review
R-003 | Employee Data | Ransomware / Attacker | Dependence on cloud-hosted data and service availability | Data exposure or service disruption | Low | High | Mitigate | Separate backup storage; recovery strategy
R-004 | HR Systems | Cloud outage / Infrastructure failure | Dependence on primary cloud environment | HR system unavailable during provider outage | Medium | High | Mitigate | BCP; DRP; alternate recovery environment
R-005 | HR Data | System failure / Human error | Backup recovery capability not yet tested | Permanent or prolonged data loss | Medium | High | Mitigate | Daily backup; restore testing