## Risk-Register.xlsx
Risk ID | Asset | Risk Description | Likelihood | Impact | Risk Level | Treatment | Control | Risk Owner | Status | Target Date
R-001 | Employee Data | Administrator account takeover because MFA is not enabled on all administrator accounts | High | High | High | Mitigate | MFA | IT Manager | Open | 30 Aug 2026
R-002 | Employee Data | Excessive administrative privileges may enable unauthorized access or data modification | High | High | High | Mitigate | Least Privilege; RBAC; Periodic Access Review | IT Manager | Open | 30 Sep 2026
R-003 | Employee Data | Cloud dependency may cause data exposure or disruption if the primary provider is compromised or unavailable | Low | High | Medium | Mitigate | Separate Backup Storage; Recovery Strategy | IT Manager | Open | 30 Sep 2026
R-004 | HR Systems | Cloud provider outage may make the HR system unavailable | Medium | High | High | Mitigate | BCP; DRP; Alternate Recovery Environment | IT Manager | Open | 30 Sep 2026
R-005 | HR Data | Untested backup recovery may result in prolonged or permanent data loss | Medium | High | High | Mitigate | Daily Backup; Restore Testing | IT Manager | Open | 30 Sep 2026