## Gap-Assessment.xlsx
Control | Current State | Gap | Status | Remediation | Evidence for Closure
MFA | MFA enabled for administrator accounts | No significant implementation gap identified | Implemented | Maintain monitoring | MFA configuration and periodic verification
RBAC / Least Privilege | RBAC implemented | Periodic access review not yet running | Partially Implemented | Establish quarterly access review | Completed review records and approval
Backup | Daily backup configured | Restore capability has not been tested | Partially Implemented | Perform restore test | Successful restore test report/logs